## PESA & ACHIRE TRACKER
PESA & ACHIRE ACTION TRACKER
| Action Item | Closure date | Responsible person | Comment on status | RAG Status
1 | The reporting during weekly meetings from each sales officer shoud cover weekly targets vs actual peformance, reasons for deviation and corrective measures to meet target. | 27.09.22 | Natasha, Peter & Kachenje | C.E.O has refined this action point, corrected the action owner plus included new owners and closure date revised from 19/09 to 27/09. | Open
2 | Apply for Consultancy Tender | 24.10.22 | Chobela | Last discussion was that you need to have a number of Tenders shortlisted for discussion with General Manager for ABS to consider participating in. | WIP
4 | Share in a worksheet your deal pipeline with names and amounts of prospective customers for PESA. | 16.9.22 | Kachenje |  | Open
5 | Share Corporates targeted for ABS services with names and contact details of liaison, preferably CFO or Finance Manager. | 16.9.22 | Chobela |  | Open
6 | Create File Repository and input means of access of data | 23.9.22 | Chobela |  | Open
7 | Take Mifi to Zamtel | 19.9.22 | Natasha |  | Open
| Share list of the 22 individuslas with James containing the Geographical position of debtors | 12.9.22 | Cynthia |  | WIP
| Create mobile app for smarrt collections and send into production. | 01.10.22 | Chobela |  | Open
| Make rota for social media responses. Kachenje observed that the teams efforts were not well streamlined. She was working on a strategy that coverscustomer service which she would share in detail in the next meeting. | 27.09.22 | Kachenje |  | Open
| Approval of commission for lead generation amount to be agreed upon away from main contract. There is an existing contract for agents that can be shared with two identified officials. | 23.9.22 | Natasha |  | Open
| ALSTRALZ TECHNOLOGIES LTD yet to confirm approval of draft MOU sent | 23.9.22 | Natasha |  | Open
| Look into BigTree and Trade Kings to sign with us | 30.09.22 | Natasha |  | Open
| Isi advised that if there were items not posted, within 24hrs of disbursement as per norm, Credit must ensure that these are promptly regularized or escalate to the C.E.O for resource deployment to avert potential loss of revenue and capital from poor record keeping. All outstanding items outside LMS to be posted within the week. | 23.9.22 | Lottie |  | Open
| Shadreck said that there loans 5 PTPs and restructures to be done. | 23.9.22 | Shadreck |  | Open
| Isi advised that a professional presentation with accurated stats was expected at weekly meetings going forward. |  | Lottie |  | Open
| Add Shadreck and Lottie to the facebook page for improved responses to queries and credit decisioning. | 23.9.22 | Kachenje |  | Open
| Touchbase with Mary on Customer satisfaction assessment | 30.09.22 | Isi |  | Open
| Isi stated that having a functional landline is compliance matter (BOZ). It was a bare minimum before venturing into telephone call handling. The landline needs to be reconnected urgently. Natasha to follow up withZamtel on our landline | 23.9.22 | Natasha |  | Open
| Kachenje would be expected to follow through the providing training on how to handle phones as part of customer service. Conduct training and draft short policy on telephone handling. | 30.09.22 | Kachenje |  | Open
| Sales team should share a Deal pipeline with names and amounts of loans with tentative dates of disbursements and probability of success. Kachenje to report on this weekly. | 26.09.22 | Kachenje |  | Open
| Kachenje observed that the teams efforts were not well streamlined. She was working on a strategy that coverscustomer service which she would share in detail in the next meeting. | 27.09.22 | Kachenje |  | Open
| Lucky to have an offline 15-20 minutes chat with Joshua to assist him on negotiation skills and collections strategies to improve the performance. | 23.9.22 | Lucky & Joshua |  | Open
| He said the Creation of a repository for sharing of data was in progress and would be completed in the course of the week. | 23.9.22 | Chobela |  | Open
| Obtain two more instructions for repos within the course of the week. | 23.9.22 | Chobela |  | Open
| Isi asked to see the stats so far on SMS sent by both PESA and Achire. | 23.9.22 | Chobela